## Acceptance Criteria Draft
Project Charter | [8 empty] | RACI MATRIX (to be filled by Project Manager)
Project Title |  | Enterprise AI Meeting Assistant & Microsoft Teams Calling Bot (TDA Bot) |  |  | Planned Benefit ( in Rs. Lakhs) |  |  |  | RACI (R - Responsible A - Accountable C - Consulted I - Informed) | Planning & Definition |  |  |  | Execution |  |  |  | Implementation & Closure |  |  |  | Member Name
Project Start Date |  | 2026-07-07 |  |  | Type of benefit |  |  |  |  | PM Plan | Resource Plan | Project Schedule | Functional Requirement | Data Collection | Data Assessment | Data Processing | Model Development & Validation | Solution Deployment | Project & Training Material | Transition | Project Closure | Responsible Person
Customer's Desired Target Date |  |  |  |  | Project Cost (in Rs. Lakhs)
DICE Score (filled by Project Manager) |  |  |  |  | Funding Limit from Customer (in Rs. Lakhs)
Team | [5 empty] | Business Approval
CP |  | Soummo Bose |  |  |  | Sponsor - BUSINESS |  | Soummo Bose / Tata Steel Leadership
CAM |  | Susnata Das / Nitish Kumar |  |  |  | Business Lead |  | Susnata Das
Project Manager |  | Nitish Kumar / Susnata Das |  |  |  | TRC (Optional) |  | Tata Steel Information Security & Enterprise Architecture Group
BTS Team |  | Susnata Das, Nitish Kumar, Soummo Bose | [5 empty] | Tata Steel IT Projects & AI Automation Team
Implentation Partner (if any) |  | In-House Development (Tata Steel IT Projects & AI Automation Team)
Business Need/ Objective | [8 empty] | Project Sponsors | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Chief IT Projects / IL2 and above
Deploy an enterprise automated Microsoft Teams Calling Bot (TDA Bot) that automatically attends enterprise meetings, captures real-time unmixed audio and synchronized video feeds via Microsoft Graph Calling SDK and Skype Media Platform, transcribes speech with speaker diarization using OpenAI Whisper, and generates structured Minutes of Meeting (MoM) documents in Word (.docx) format delivered directly to meeting organizers. The system is engineered for enterprise scale, supporting 100 concurrent meetings and 1,000 daily meetings across Tata Steel. The solution eliminates manual note-taking overhead (saving 2,000 - 4,000 employee hours daily across 1,000 meetings), ensures 100% compliance recording, centralizes meeting knowledge in Google Cloud Storage (GCS) and Google BigQuery, and supports seamless command-based control (@TDA #joinv2, #status, #stop, #leave) with real-time visual mascot status feedback. | [8 empty] | Steering Committee | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar | Soummo Bose, Susnata Das, Nitish Kumar
Project Scope | [5 empty] | Deliverables/ Product Description |  |  | CP/ CAM
The project encompasses the end-to-end development, hardening, and deployment of the Teams Calling Bot ecosystem: 1. Development and deployment of Windows-based Calling Service (.NET Framework 4.7.2 x64) leveraging Microsoft.Graph.Communications.Calls.Media and Skype.Bots.Media. 2. Azure Bot Service (Node.js) front-channel messaging controller for Teams chat commands (@TDA #joinv2, #status, #help, #leave). 3. Real-time multi-stream unmixed audio capture (PCM 16kHz, 16-bit mono per speaker) and 720p/1080p synchronized screen video recording. 4. Pre-warmed visual mascot face card broadcast in the meeting video stream to visually notify participants that recording is active. 5. Automated speech-to-text pipeline utilizing OpenAI Whisper with multi-speaker diarization and timeline synchronization. 6. LLM-powered MoM summarizer generating executive summaries, discussion points, and action items in Microsoft Word (.docx) format within 5 minutes. 7. Secure archival of audio, video, transcripts, and MoM files in Google Cloud Storage (GCS) with BigQuery audit telemetry. 8. High-concurrency enterprise architecture supporting up to 100 concurrent meetings and 1,000 daily meetings with Google Cloud Firestore distributed locks. 9. Comprehensive Information Security controls: tenant isolation, SRTP media encryption, TLS 1.3, mTLS certificate authentication, zero persistent local VM media storage (immediate purge post-GCS upload). | [5 empty] | 1. Production-ready Teams Calling Bot Service (.NET 4.7.2 x64) hosted on Tata Steel Windows Virtual Machines. 2. Azure Bot Service messaging gateway and Microsoft Teams App Manifest integrated into the Tata Steel tenant. 3. High-performance unmixed PCM16K audio recorder and 720p/1080p video capture subsystem. 4. Live in-call mascot video card generator providing visual recording transparency. 5. Automated Whisper transcription engine and Word (.docx) MoM generation pipeline. 6. Google Cloud Storage bucket architecture with lifecycle retention policies and BigQuery analytics registry. 7. Complete technical architecture documentation, user playbook, and Infosec security assessment compliance package. |  |  | Management Approver | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Soummo Bose | Chief IT Projects
Background | [8 empty] | SME | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Implementation Partner / SME / CAM
Tata Steel employees and leadership conduct hundreds of critical operational reviews, governance committees, and cross-functional project meetings daily, scaling up to 1,000 daily meetings enterprise-wide. Manual note-taking is inconsistent, labor-intensive (costing 2-4 hours per meeting), and delays action item tracking by days. Previous browser-based bots (e.g. Playwright / headless Chromium) suffered from severe latency (>30-45 seconds join time), audio stutter, high resource contention, and could not scale past 5 concurrent calls. The Teams Calling Bot (TDA Bot) utilizes native Microsoft Graph Communications Calling SDK and Skype Media Platform to provide sub-3-second join times, isolated unmixed PCM audio per speaker, high-reliability video recording, robust capacity for 100 concurrent meetings and 1,000 daily meetings, and immediate automated MoM delivery with enterprise-grade security. | [8 empty] | Project Manager | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | Nitish Kumar / Susnata Das | From Projects Team
As Is Process/ System | [5 empty] | To Be Process/ System |  |  | PMO
- Manual note-taking and minute preparation by meeting attendees, consuming 2-4 hours per meeting. - Inconsistent MoM quality and delayed distribution (often 24-72 hours after meetings). - Action items, decisions, and discussions are often unrecorded or lost in personal notebooks. - Meeting recordings (if manually enabled) are siloed in individual OneDrive/SharePoint folders without centralized governance, lifecycle policies, or searchable transcripts. | [5 empty] | - Fully automated meeting attendance via calendar schedule or simple in-chat summon (@TDA #joinv2). - Real-time unmixed audio recording per speaker with live visual mascot card confirming recording. - Automatic AI transcription (Whisper) and structured MoM generation (.docx) within 5 minutes post-call. - Centralized, encrypted storage of recordings and MoMs in Tata Steel GCS with BigQuery metadata indexing. - Searchable transcripts, automated action item extraction, and strict enterprise security governance. |  |  | CDBA
Design of the system | [5 empty] | KPIs (UoM, Baseline and Target) |  |  | CQA
3-Tier Hybrid Enterprise Architecture: 1. Front-Channel Signaling Gateway: Azure Bot Service (Node.js) receiving Microsoft Teams user activities and bot commands (@TDA #joinv2, #status, #leave). Dispatches join intents to Calling Service. 2. Media Platform Calling Bot Core: Hosted on dedicated Windows Server / Windows 11 Enterprise VMs. Built on .NET Framework 4.7.2 x64 using Microsoft.Graph.Communications.Calls.Media and Skype.Bots.Media. Handles real-time SRTP audio/video sockets, captures unmixed 16kHz PCM audio per speaker, records 720p/1080p screen video, and broadcasts a live animated mascot video card into the meeting feed. 3. Post-Processing & Intelligence Pipeline: Automated Whisper transcription engine, Claude/LLM MoM synthesizer, and Word (.docx) generator. 4. Storage & Archival Layer: Google Cloud Storage (GCS) for media/transcript/MoM storage with automated retention lifecycle policies, Google BigQuery for analytics and audit indexing, and Google Cloud Firestore for distributed concurrency locking. | [5 empty] | 1. Bot Join Latency: Baseline = 30-45s (browser-based bot) ¦ Target = < 3.0s (Calling SDK native join). 2. Concurrency & Daily Throughput: Baseline = 5 calls ¦ Target = 100 concurrent meetings and 1,000 daily meetings processed on VM cluster. 3. MoM Turnaround Time: Baseline = 2-4 hours manual ¦ Target = < 5 minutes automated post-call. 4. Audio & Video Quality: Baseline = mixed low-quality audio ¦ Target = 16kHz unmixed PCM audio & 720p/1080p video. 5. System Availability / Uptime: Baseline = 95.0% ¦ Target = 99.9% uptime with automated health checks. 6. Infosec Compliance: Baseline = Partial ¦ Target = 100% compliance with Tata Steel Infosec & Cloud Security Baseline. |  |  | Project Team Members | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal | Susnata Das, Nitish Kumar, Shomick Roy, Jaidev Lal
Issues/Risk | [5 empty] | Assumption/Dependency
1. Risk: Microsoft Graph API rate-limiting during high concurrent call summon bursts. Mitigation: Implemented exponential backoff and 1.5-second staggered join queues. 2. Risk: Multiple users summoning the bot to the same meeting causing duplicate joins. Mitigation: Google Cloud Firestore distributed lock keyed by normalized meetingId / thread.v2 hash. 3. Risk: VM disk space exhaustion during long multi-hour video recording sessions. Mitigation: High-speed streaming buffers with automatic local media file purge immediately upon successful GCS upload and SHA-256 integrity verification. 4. Risk: Unintended meeting joining or eavesdropping. Mitigation: Strict tenant isolation (Tata Steel AAD tenant only), explicit in-call visual recording mascot card, and chat control commands (#leave). | [5 empty] | 1. Azure AD Application with approved Graph Application Permissions: Calls.Join.All, Calls.Media.All, Calls.AccessMedia.All, and OnlineMeetings.Read.All. 2. Valid Public FQDN with trusted CA-signed SSL/TLS certificate (CN matching bot domain) for Graph calling webhook callbacks on port 8445/8611. 3. Enterprise firewall rules allowing TCP 8445/8611 incoming from Microsoft Graph Calling CIDRs and UDP media port range (50000-60000) for real-time SRTP streams. 4. Google Cloud Platform service account credentials with scoped access to GCS buckets, BigQuery datasets, and Firestore databases. 5. Project leadership and governance under Susnata Das, Nitish Kumar, and Soummo Bose.
Technology Plan
ITS 209 Technology Plan to be attached
Project Sign Off (ITS 150 form to be attached)
Customer's Acceptance Criteria |  |  |  | Approver Name |  |  | Approval Date | Approver Title
Tata Steel Enterprise Customer Acceptance Criteria for Teams Calling Bot (TDA Bot): 1. Call Join Latency: Bot must join scheduled or ad-hoc Teams meetings within 3.0 seconds of receiving @TDA #joinv2 command or calendar trigger. 2. Visual Recording Transparency: Bot must broadcast a live mascot video stream throughout the call displaying recording status, meeting title, and active duration. 3. Media Quality & Completeness: Capture 100% of meeting audio as unmixed 16kHz 16-bit PCM streams per participant without clipping, dropouts, or downmixing distortion. Capture synchronized video up to 1080p. 4. Scalability & High Concurrency: Bot infrastructure must successfully support up to 100 concurrent meetings simultaneously and a daily throughput of 1,000 meetings per day with < 1% CPU jitter, < 5 min MoM delivery, and 99.9% uptime. 5. AI Transcription & MoM Delivery: Automated Whisper transcription with speaker identification, followed by structured MoM generation in Word (.docx) format delivered to the organizer within 5 minutes of meeting termination. 6. Cloud Archival & Searchability: All meeting recordings, transcripts, and MoM summaries automatically archived in Google Cloud Storage with full metadata indexed in Google BigQuery (sized for 1,000 meetings/day). 7. Infosec & Security Assessment Compliance: Zero persistent raw media retention on local VM disk (automatic purge post-GCS upload); full SRTP media encryption; TLS 1.3 for all REST/webhook traffic; mTLS certificate authentication; strict Tata Steel tenant-only isolation. |  |  |  | Soummo Bose |  |  |  | Sponsor / Chief IT Projects
|  |  |  | Susnata Das |  |  |  | Business Lead
|  |  |  | Soummo Bose |  |  |  | CP
|  |  |  | Nitish Kumar |  |  |  | BTS Lead / Solution Architect
|  |  |  | Tata Steel Information Security Team |  |  |  | Infra & Security Approver
Project Milestones Schedule (to be filled by Project Team)
S.No. | Milestones | Planned Start Date | Planned End date | Actual Start date | Actual End Date |  | Remarks
| Analysis | 2025-12-01 | 2025-12-05 | 2025-12-01 | 2025-12-06
| Design | 2025-12-06 | 2025-12-12 | 2025-12-07 | 2025-12-14
| Development | 2025-12-13 | 2026-01-10 | 2025-12-15 | 2026-01-15
| Implementation | 2026-01-11 | 2026-01-15 | 2026-01-16 | 2026-01-25
| Go-Live | 2026-01-16 | 2026-01-20

## Annexure
Calculation of DICE SCORE
A DICE score serves as indicator of the likely success of a project. DICE stands for: Duration (D): either the total duration of short projects, or the time between two milestones on longer projects Team Performance Integrity (I): the project team's ability to execute successfully, with specific emphasis on the ability of the project leader Commitment (C): levels of support, composed of two factors: C1 visible backing from the sponsor and senior executives for the change C2 support from impacted party by the change Effort (E): how much effort (in percentage terms) will it require to implement (above and beyond business as usual) The DICE score is calculated as: D + (2 x I) + (2 x C1) + C2 + E Duration Team Performance Integrity < 2 months = 1 Very good = 1 2-4 months = 2 Good = 2 4-8 months = 3 Average = 3 > 8 months = 4 Poor = 4 C1 Commitment (Senior Management) C2 Commitment (Local) Clearly and strongly communicate the need = 1 Eager = 1 Seem to want success = 2 Willing = 2 Neutral = 3 Reluctant = 3 Reluctant = 4 Strongly Reluctant = 4 Effort < 10% additional = 1; 10-20% additional = 2; 20-40% additional = 3; > 40 % additional = 4 DICE score can be categorized in following 3 ways: 1. DICE score between 7 - 14 is in the "Win" Zone (very likely to succeed) 2. DICE score between 14 - 17 falls in the "Worry" Zone (hard to predict success) 3. DICE score higher than 17 falls in the "Woe" Zone (high unpredictability or likely to not succeed).
RACI Matrix
RACI Matrix describes the participation by various roles in completing tasks/ deliverables for a project. It is useful in clarifying roles and responsibilities in cross-functional projects and processes involving multiple stakeholders. RACI acronym pertains to four key responsibilities: Responsible (R), Accountable (A), Consulted (C), and Informed/ Interested party (I). Responsible: Those who do the work to complete the task. There is at least one role with a participation type of responsible, although others can be delegated to assist in the work required. Accountable (also Approver): The one ultimately answerable for the correct and thorough completion of the deliverable/ task, and the one who delegates the work to those responsible.There must be only one accountable specified for each deliverable/ task. Consulted: Those whose opinions are sought, typically subject matter experts. Informed: Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
Sign off
Sign off needed by following stakeholders with respect to project charter document: 1. Sign off needed by sponsor for KPIs and acceptance criteria. 2. Sign off by the BTS team. 3. Sign off by the CP. 4. Sign off by the Infra. Document to be attached and signed by all the stakeholders indicating their agreement to the KPIs, acceptance criteria, scope, etc. as mentioned in the project charter document. Refer to the "acceptance form" as attached.